## Requirements Matrix
ID | Category | Requirement | Responsible Person | Priority | Status | Action Required
REQ-01 | Catalog Data | Finalize 85 product catalog items (EN & TA names, pricing & variants) | Dev | Critical | Completed | Seeded into backend/prisma/seed.ts dataset.
REQ-02 | Photography | Collect product photos & remove background clutter (White background) | GM | High | In Progress | Photograph items; remove backgrounds with PhotoRoom / Remove.bg.
REQ-03 | Image Storage | Create Cloudinary account & setup product image upload preset | Dev | High | Live Ready | Cloudinary credentials & upload middleware configured.
REQ-04 | Hosting Plan | Purchase Hostinger VPS plan (Ubuntu 22.04 LTS - India Location) | Client | Critical | Pending | Client to buy Hostinger KVM VPS plan.
REQ-05 | Database Setup | Create PostgreSQL database on Hostinger VPS & link DATABASE_URL | Dev | Critical | Live Ready | PostgreSQL setup script & Prisma config prepared.
REQ-06 | Domain Purchase | Purchase domain name (.in or .com) via Hostinger / Namecheap | Client | Critical | Pending | Client to register domain name.
REQ-07 | DNS & SSL | Point Domain DNS A-Records to Hostinger IP & issue free SSL cert | Dev | High | Ready | Configure Nginx reverse proxy & Certbot SSL.
REQ-08 | Live Deploy | Run database migrations & seed 85 products to production database | Dev | Critical | Ready | Execute npx prisma db seed on live VPS.
REQ-09 | Payment Gateway | Integrate Razorpay / Cashfree UPI & Card online payments | Dev | Medium | Phase 2 (Hold) | On Hold for Phase 2 as instructed.
REQ-10 | Shipping Gateway | Integrate Shiprocket courier dispatch API & tracking | Dev | Medium | Phase 2 (Hold) | On Hold for Phase 2 as instructed.
REQ-11 | Local Pincodes | Set up South India pincodes & flat delivery rates | Dev | High | Completed | Seeded Chennai, Madurai, Kovai, Trichy, Blr pincodes.
REQ-12 | Admin Security | Setup admin credentials (admin@yathu.com) & JWT authentication | Dev | Critical | Live Ready | CMS routes secured with JWT role authorization.
REQ-13 | Admin SOP | Prepare guide for adding/editing products & updating prices | Dev | High | Completed | Documented in MASTER_SETUP_AND_PRODUCT_OPERATIONS_GUIDE.md.
REQ-14 | DB Backups | Setup automated daily PostgreSQL database backups | Dev | High | Ready | pg_dump automated cron script created.